## Project Tracker
Task | Start Date | End Date | Owner | % Complete | Status
Define Scope | 2025-10-01 | 2025-10-05 | Alice | 100 | Done
Design UI | 2025-10-06 | 2025-10-12 | Bob | 60 | In Progress
Build Backend | 2025-10-13 | 2025-10-25 | Charlie | 20 | Not Started
Testing | 2025-10-26 | 2025-10-31 | Alice | 0 | Not Started