## Sheet1
Task | Owner | Start | End | % Complete | Status
Site Survey | PM | 2025-10-01 | 2025-10-04 | 100 | Done
Vendor Selection | Procurement | 2025-10-05 | 2025-10-09 | 80 | In Progress
Store Renovation | Construction | 2025-10-10 | 2025-10-19 | 50 | In Progress
IT Setup | IT | 2025-10-20 | 2025-10-24 | 20 | Not Started
Go-Live | Ops | 2025-10-25 | 2025-10-30 | 0 | Not Started